## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _ADM_UserAccess_27
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | page name(HEADER) | OMS _ADM_UserAccess_27 | DEFECT_231 | both in a admin tab and page should have a same header text | but in a tab has User Access and in a page it has a USER ACCESS CONTROL | FAIL | make it similar in both | 2017-12-07
2 | tab Operation | OMS _ADM_UserAccess_27 | DEFECT_232 | tab should work in a proper series | its ntt in a proper | FAIL | make it proper series tab operation | 2017-12-07
3 | TREE SEARCH | OMS _ADM_UserAccess_27 | DEFECT_233 | its should search and filter a page no records found a tree tab should get empty and should display NO RECORDS FOUND MESSAGE | its filtering a file as per but when no records found a tree tab shouldn't get empty and dint display a NO RECORDS FOUND MESSAGE | FAIL | make it to display a proper message here when no records found | 2017-12-07
4 | SEARCH | OMS _ADM_UserAccess_27 | DEFECT_234 | al the time a search should filter properly | btt here first time a search wil happen if I click and view a particular file if I search again it trhrowing some error | FAIL | make it to search all the time properly | 2017-12-07
5 | refresh | OMS _ADM_UserAccess_27 | DEFECT_235 | add a feature refresh button in this page | implementa a feature here |  | add a refresh button feature | 2017-12-07
6 | sort a records in GRID | OMS _ADM_UserAccess_27 | DEFECT_236 | in a grid all the times records should display in a sorting order | its ntt a proper a make it to display in a sorting order | FAIL | make it to display in a proper order so that can access easily | 2017-12-07
7 | Export user access | OMS _ADM_UserAccess_27 | DEFECT_237 | when exporting exported success fully message should display | its not showing any successfully exported message | FAIL | display a successfully exported message here | 2017-12-07
8 | import user access | OMS _ADM_UserAccess_27 | DEFECT_238 | when import uesr access imported success fully message should display | its not showing any successfully exported message | FAIL | display a successfully exported message here | 2017-12-07
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: