## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _emp_alrtnotes_tab3_22_2
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | cursor focusing | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_204 | cursor should focus in a first field | its ntt focusing any where make it to show a focus in a First Field | CONFUSED | show a focus in a First Field | 30/06/2017
2 | Instruction/note SEARCH | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_205 | when text Enters it should filter properly | btt this search field not working properly | FAIL | search should filter | 30/06/2017
2_1 | Instruction/note SEARCH | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_205_1 | when searching ifno records found it should display a NO RECORDS FOUND mesaage | no its ntt showing a any message | FAIL | display a message | 30/06/2017
3 | Submit button | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_206 | when any of the fields dint select itl should notify a error message | btt here notifying messsage to order type and county state name but its not notifying a message instruction field also its getting message record inserted successfully message and even record also ntt their in a grid | FAIL | cross verify and fic as soon | 30/06/2017
4 | view/update from a grid | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_207 | when I click and view a record it should enable a edit/update button if I click it should show a message record updated successfully | but here if I click and view a record from a grid edit/update button not enabling but if I click on submit button its displaying a message that record added successfully but even if a made a changes in a viewed file its displaying message record update successfuly but stil its adding a new record into a list | FAIL | jst cross verify and fix it | 30/06/2017
5 | delete button | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_208 | when I click on delete button a record selected should get delete and should show a message that a record deleted successfully | but here delete operation itself not happening | FAIL | make a record to delete when clicked on it | 30/06/2017
6 | All Ordertype/state/County Grid | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_209 | what is a use of this Grid when itll use | ???? | CONFUSED | doubt | 30/06/2017
7 | mandate Fields | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_210 | all the mandate Fields should display with* symbol | but here none of the fields notifying with a *symbol | FAIL | mandate Fields should display with* symbol | 30/06/2017
8 | refresh | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_211 | when moving from 1 tab to another tab a page should get refresh | its nt happening | FAIL | when move from 1 tab to another page should get refresh | 30/06/2017
9 | maximiztion | OMS _emp_alrtnotes_tab3 _22_2 | DEFECT_212 | enable maximization and paginationsd should be proper | align properly |  | enable maximization | 30/06/2017
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: