## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | vendor -Client instructions_tab2
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | label text | vendor -Client instructions_tab2 | DEFECT_281 | Search Text box should have a label Search Vendor Order Type | but here no Text label ha sbeen displaying here | FAIL | make it to display a search vendor order type label | 25/7/2017
2 | search text | vendor -Client instructions_tab2 | DEFECT_282 | when a client subclient selected bellongs to that instructions will be displaying in a below grid can search and filter | search happening properly but if I doesn’t have any records in a below grid if simply mouse cursor goes around a text box its self showing no records found | FAIL | confused about this is it k r wt verify about this | 25/7/2017
3 | submit button | vendor -Client instructions_tab2 | DEFECT_283 | when click on submit if have a any mandate fields missing should display a proper Error message | if any mandate fileds missing a Error messagwe displaying at the same time its showing Instruction inserted successfully message also even have a error also | FAIL | cross verify and make it proper | 25/7/2017
4 | mandate fields | vendor -Client instructions_tab2 | DEFECT_284 | mandate fields dint fill mean when submiting throw a error and indicate that with a * | * butt here no mandate fields are indicated | FAIL | display a * on mandate fields | 25/7/2017
5 | clear button | vendor -Client instructions_tab2 | DEFECT_285 | when click on a clear button al the fields should get clear | butt here only a text box getting clear confused cross verify about this | CONFUSED | cross verify about this | 25/7/2017
6 | delete button | vendor -Client instructions_tab2 | DEFECT_286 | when click on a delete button a record should get delete and notify a confirmation and successful message | 1.)btt here when click on a delete button confirmation messge has been displaying and if I click on a yes success fully deleted message also displaying but no record has been deleted from a grid 2.) at the same time text viewed in a tEXTBOX doesn’t get cleared after deletion also | FAIL | a record getting delete only when a record is viewed in a editing mode make it to delete when click on delete button anytime | 25/7/2017
7 | DUBLICATION | vendor -Client instructions_tab2 | DEFECT_287 | for the same client subclient should have same instruction dublication | but here its accepting a dublication | FAIL | make it tnot to accept a dublication | 25/7/2017
8 | maximize | vendor -Client instructions_tab2 | DEFECT_288 | make it to page should be maximized by defualt | make it | FAIL | make it maximized | 25/7/2017
9
10
11
12
13
14
15 |  | DEFECT_289
16
17
18
19
20
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: