## level11
Titlelogy App DEFECT REPORT
PROJECT NAME |  |  | TitleLogy App |  | DEFECT REPORT belongs to TEST case Name&No: | TLGY_Create Users-3
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | AJITH
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | Confirm Password | TLGY_Create Users-3 | DFC_11 | Its should be same as password then oly page should submit if not it should throw a error | but here u can giv watever u want if a password and confirm password doesn’t match also page wil get submit Even if u left this field blank also page gets submit | FAIL | cross verify about this | 2017-05-07
2 | mandate Fields | TLGY_Create Users-3 | DFC_12 | in this page (Email,First Name,Password,Confirm Password ) are the mandate fields if any of a field left blank its should display error message | but here confirm password if doesn’t match or if field left it blank also it wont throw any error | FAIL | madate and match a Confirm password filed | 2017-05-07
3 | Submit button | TLGY_Create Users-3 | DFC_13 | when a submit button click its should show a progress message that loading | bt here its showing updating message on progress | FAIL | make it to display a progress message Loading | 2017-05-07
4 | Submit button | TLGY_Create Users-3 | DFC_14 | once a submitted display a message user Created Successfully | but here its showing a message updated success full | FAIL | change a message here | 2017-05-07
5 | cancel | TLGY_Create Users-3 | DFC_15 | a page should get cancel | but here its nothing happening | FAIL | ?? | 2017-05-07
6 | Dublication | TLGY_Create Users-3 | DFC_16 | its shouldn’t accept a data dublication of records | but here in a same data can create n number of recoreds | FAIL | make it unique | 2017-05-07
7 | Update button | TLGY_Create Users-3 | DFC_17 | when a user viewed if I click on update (USER Updated successfully )Message should display | btt here only a update successful message displaying | FAIL | display a proper message | 2017-05-07
8 | Update button | TLGY_Create Users-3 | DFC_18 | once a updation done its should back to a Users list page | its ntt getting refresh and not getting back only | FAIL | make it to go back and refresh a page | 2017-05-07
9 | Delete Button | TLGY_Create Users-3 | DFC_19 | confirmation yes/no message should display | btt here no confirmation showing | FAIL | display a message when clicks | 2017-05-07
10 | Delete Button | TLGY_Create Users-3 | DFC_20 | when deleting if I confirmed yes its should show a progress bar Deleting and show a message deleted successful | here delete button itself not working | FAIL | display a proper message | 2017-05-07
11 | Refresh | TLGY_Create Users-3 | DFC_21 | each time if I drag page should get refresh | but here its not refeshing if I want a updated data should go back 2 dashboard and open again | FAIL | make it refresh on drag n drop | 2017-05-07
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## level2
Titlelogy App DEFECT REPORT
PROJECT NAME |  |  | TitleLogy App |  | DEFECT REPORT belongs to TEST case Name&No: | TLGY_Create Users-3
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | AJITH
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | Submit button | TLGY_Create Users-3 | DFC_106 | once a page submitted its refresh and back to a users list and display user list | but here itll stay in a same page itself | FAIL | make it to referesh a page | 31/7/2017
2 | update button | TLGY_Create Users-3 | DFC_107 | once a page update button clicks its refresh and back to a users list and display user list | but here itll stay in a same page itself | FAIL | make it to referesh a page | 31/7/2017
3 | delete button |  | DFC_108 | remove a delete button when a user viewed | remove it no need here | FAIL |  | 31/7/2017
4 | Delete Button | TLGY_Create Users-3 | DFC_109 | confirmation yes/no message should display | btt here no confirmation showing | FAIL | display a message when clicks | 31/7/2017
5 | Delete Button | TLGY_Create Users-3 | DFC_110 | when deleting if I confirmed yes its should show a progress bar Deleting and show a message deleted successful and page should get refresh | buu here showing progress bar updating and user deleted message also ntt displaying and then its nt refreshing a list | FAIL | display a proper messages and refresh a page | 31/7/2017
6 | Refresh | TLGY_Create Users-3 | DFC_111 | each time if I drag page should get refresh | but here its not refeshing if I want a updated data should go back 2 dashboard and open again | FAIL | make it refresh on drag n drop | 31/7/2017
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25