## DFR _client order cost _15
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _client order cost _15
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | SUDHAKAR
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | Header text | OMS _client order cost _15 | DEFECT_109 | a text in a header and a masters should be a same | its different in a masters and headers | FAIL | plese make it same in all the place so that a classification will be easy | 2017-07-06
2 | Cursor Focus To First Field | OMS _client order cost _15 | DEFECT_110 | when page opens itself a cursor should display into a first field by defualt | but by defualt cursor not displaying | FAIL | cross verify about this | 2017-07-06
3 | client name_label text | OMS _client order cost _15 | DEFECT_111 | text label in a dropdown list should display as SELECT | btt here its displaying lik a ALL | FAIL | change a label into a Select | 2017-07-06
4 | Order Type | OMS _client order cost _15 | DEFECT_112 | madate fields should display with a res asterisk mark should display | butt here it’s a mandate field but asterisk mark was not there | FAIL | make a *mark to display beside a filed | 2017-07-06
5 | Refresh button>Edit | OMS _client order cost _15 | DEFECT_113 | when we click a refresh button its should refresh a page of all fields | butt here all the fields getting clear even while Editing a particular record a EDIT button by defualt doesn’t altering | FAIL | cross verify and fix it about this | 2017-07-06
6 | TAB operation | OMS _client order cost _15 | DEFECT_114 | all the records available in a list should be in a proper sorting order | list of records displayin a particular sorting order | CONFUSED | cross check about this | 2017-07-06
7 | DELETE OPTION | OMS _client order cost _15 | DEFECT_115 | as I discussed with a sir please add a DELETE button to this page because if needed to delete a record already available from a GRID there should be a delete option |  | ENHANCE&Add New Feature | ADD A NEW FEATURE | 2017-07-06
8 | searching in a GRID | OMS _client order cost _15 | DEFECT_116 | when searching if no records found it should throw a no records found message | SEARCH WORKING nicely but only thing is when a no record found in a search No message has been displaying | FAIL | Add a no records found message to this search | 2017-07-06
9 | maximize | OMS _client order cost _15 | DEFECT_117 | when a maximize button clicks page should maximize and all the page Fields should allign properly | butt page has been maximizing and fileds are not alliging a properly | FAIL | jst allign all the field tabs as per a maximize screen | 2017-07-06
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## LEVEL _2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _client order cost
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | GRID Alignment | OMS _client order cost _15 | DEFECT_117_1 | Grid Alignment should be proper for al the fields | btt here alignment is not proper and make a better utilization of Grid | FAIL | just make it smal tab for SI.NO And Make it to display a ORDER COST in a GRID tab | 17/7/2017
2 | Client name | OMS _client order cost _15 | DEFECT_117_2 | client name ALL button represents selecting all clients so if I submit a page its should reflect to al the clients | but here when am selecting a All Also when submiting a page it used to show select a Client name message | CONFUSED | cross verify about this | 17/7/2017
3 | Subclient name | OMS _client order cost _15 | DEFECT_117_3 | when I select a client name a Subclient belongs to that client should display and if I select a 1 subclient data should save to that particular sublient name only | but here when am submitting a record if I select a 1 subclient when submitting its also submiting and creating other subclients of that particular client at the time of updation also happrening a same | FAIL | cros verify about this | 17/7/2017
4 | Delete button | OMS _client order cost _15 | DEFECT_117_4 | when click on delete a record should get delete an should display a confirmation and successful message | both successful and confirmation message has been displaying but here if I delete a 1 record same like creating deleting a mulltiple subclients same time | CONFUSED | make it proper | 17/7/2017
5 | Search By a selected | OMS _client order cost _15 | DEFECT_117_5 | search should filter a data and if I click on a view file should view here | but here when I search a Record Grid Varying A tabs its should view a record to edit Throwing some error | FAIL | Allign a grid properly when searching | 17/7/2017
6 | Search by Button | OMS _client order cost _15 | DEFECT_117_6 | when page viewed itself by defualt should display a Select label on that button | by defualt it display a nothing | FAIL | make it to display a Select and make it to display a capital SELECT similar to al forms | 17/7/2017
7 | SAVE button Label | OMS _client order cost _15 | DEFECT_117_7 | as per all a forms ADD label text should display | but here a Save label text displaying | FAIL | change a label text and make it similar to other pages also | 17/7/2017
8 | maximazion issue | OMS _client order cost _15 | DEFECT_117_8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet3
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: