## DFR_SubClients 06
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _SUBCLIENT_06
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | DEVELOPER DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | OMS_SUBCLIENT/Client Name SELECT from a dropdown | OMS_SUBCLIENT_06 | DEFECT_46 | in a dropdown tab by defualt selectlabel should display before clicks | in a dropdown tab instead of SELECT ITS Displaying a ALL | FAIL | chage into select instead of all but as I discussed to sir in this place not mandatory leav it | 27/05/2017 |  |  | KAVITHA
2 | OMS_SUBCLIENT/Instructions | OMS_SUBCLIENT_06 | DEFECT_47 | in a Instruction file it should accept only a data file files like(ex:.txt,.doc,.xls) | But Its accepting what ever a file if we select | FAIL | should fix oly to accept a (ex:.txt,.doc,.xls)format files | 27/05/2017 |  |  | KAVITHA
3 | OMS_SUBCLIENT/E_mail id | OMS_SUBCLIENT_06 | DEFECT_48 | it should accept only Email format | its accepting whatever a data we enter here | FAIL | change it to accept only a E_MAIL format | 27/05/2017 |  |  | KAVITHA
4 | OMS_SUBCLIENT/E_mail id | OMS_SUBCLIENT_06 | DEFECT_49 | it should accept only Email format if its not formated its should notify a ERROR Message | it should accept only Email format if its not formated its should notify a ERROR Message | FAIL | prepare 1 ERROR notification message | 27/05/2017 |  |  | KAVITHA
5 | OMS_SUBCLIENT/E_mail id | OMS_SUBCLIENT_06 | DEFECT_50 | while entering e-mail id its notifiying a TAB under delete .delete(button )labels are visible in that delete text should be there | while entering e-mail id its notifiying a TAB under delete but in delete tab there is no delete label is visible | FAIL | make a delete label should visible foreach email we enter | 27/05/2017 |  |  | KAVITHA
6 | OMS_SUBCLIENT/E_mail id | OMS_SUBCLIENT_06 | DEFECT_51 | while entering e-mail id itself it is notifiying a TAB under delete but if I click on it confirmation message is notifying do you want to delete a record if I click yes the Email id selected should delete | while entering a email id if I delete its notifying a confirmation message but its not deleting it | FAIL | discuss about with a sir before fix of it | 27/05/2017 |  |  | KAVITHA
7 | OMS_SUBCLIENT/E_mail id | OMS_SUBCLIENT_06 | DEFECT_52 | there no dublications can accept in E_mail ids | accepting dublications here | FAIL | makeit to accept oly a unique files | 27/05/2017 |  |  | KAVITHA
8 | OMS_SUBCLIENT/MAXIMIZE | OMS_SUBCLIENT_06 | DEFECT_53 | if a maximize a screen tabs in screen also should maximize | But ONLY screen getting maximizing but tabs are not maximizing as for maximize apearence | FAIL | maximize a screen n check a tab allignments | 27/05/2017 |  |  | KAVITHA
9 | Cursor Focus To First Field | OMS_SUBCLIENT_06 | DEFECT_53_1 | when a page opens it should automaticaly cursor should display into a first field of form | but here its not focusing instead of a first field some where else | FAIL | make a cursor to display into a 1st place itself jst check with this | 2017-05-06
10 | Instruction file | OMS_SUBCLIENT_06 | DEFECT_53_2 | before selecting logo a path text area in a Instruction file a Text area should disable | but text area is visible oly | FAIL | should hide a path in text area before selecting | 2017-05-06
10 | Company LOGO | OMS_SUBCLIENT_06 | DEFECT_53_2 | before selecting logo a path text area in a company LOGO a Text area should disable | but text area is visible oly | FAIL | should hide a path in text area before selecting | 2017-05-06
11 | Email | OMS_SUBCLIENT_06 | DEFECT_53_3 | when passing a cursor from a tab itself should'nt disturb any message | but here when passing a cursor from a tab itselfwithout entering any data its displaying a message Email not in a format | FAIL | should display a message atleast when enters a one character and then should display a message | 2017-05-06
12 | First Letter Should Not take Space | OMS_SUBCLIENT_06 | DEFECT_53_4 | the data fields shouldn’t accpet a space in a before a Text in fields | but here accepting a space also in before a data Enters | FAIL | make it not to accept a space at before data enters in a field if without knowledge if u enters it shoul through a error Message like("space not allowed at starting of particular data in a Particular field") | 2017-05-06
13 | pagination | OMS_SUBCLIENT_06 | DEFECT_53_5 | Need to Expand a fields and display a data entered should be in that Field | Butt here some of the fileds like company name its very important thing to display fully but its hiding a data behind better expand it | FAIL | cross verify before fix it | 2017-05-06
14 | LOGO | OMS_SUBCLIENT_06 | DEFECT_53_6 | there a label name should display like a SUB PROCES LOGO | but here jst a text label with LOGO so please change a label TEXT as per | FAIL | jst go through its not mandatory | 2017-05-06
15 | mouse cursor | OMS_SUBCLIENT_06 | DEFECT_53_7 | in a Instructions & LoGO data Text area display fields no need to go cursor wen tab operation done just hide a tab | but its going through | FAIL | hide a fields stil u selects a particular file | 2017-05-06
16 | tab operation | OMS_SUBCLIENT_06 | DEFECT_53_8 | tab should go to all the fields series wise | in this page tab not going to a Invoice radio button operation | FAIL | cross check | 2017-05-06
17 | label | OMS_SUBCLIENT_06 | DEFECT_53_9 | page header name should be same has masters | but in masters it’s a Sub client but inside a form its subprocess | FAIL | as I discussed to a sir in masters change a form name itself SUB PROCESS only | 2017-05-06
18
19
20
21
22
23
24
25

## Sample Template
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet3
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: