## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | vendor -Client instructions_tab1
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | page header | vendor -Client instructions_tab1 | DEFECT_279 | page header text should be same in a both master and form | but here its varying make it a same | FAIL | make it a same Header on both | 24/7/2017
2 | label text | vendor -Client instructions_tab1 | DEFECT_280 | Search Text box should have a label Search Vendor Order Type | but here no Text label ha sbeen displaying here | FAIL | make it to display a search vendor order type label | 24/7/2017
3 | maximization |  |  | maximize a screen for better representation |  |  | make it maximize | 24/7/2017
4 | [7 empty] | 24/7/2017
5 | [7 empty] | 24/7/2017
6
7
8
9
10
11
12
13
14
15 |  | DEFECT_281
16
17
18
19
20
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: