## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | Vendor_Master_Client_Subclient_Tab_01
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | page Header | Vendor_Master_Client_Subclient_Tab_01 | DEFECT_255 | where as both Master and a farm naming should be a same | but here in masters and in a form varying |  | Make it same for better classification | 19/7/2017
2 | LABEL | Vendor_Master_Client_Subclient_Tab_01 | DEFECT_256 | must Should have a Search Vendor Clent/Subclient label here | but here no label has been placed |  | display a label here | 19/7/2017
3 | Search text Area | Vendor_Master_Client_Subclient_Tab_01 | DEFECT_257 | 1.)Entered text should display a properly with black color 2.)and search filter should happen properly 3.)if no records found message should display 4.)and then as per a search filter Total Records value should change` | Everything working fine but here the data typing in a TEXT area displaying in a gray color make it to display in a black color AND BETTER TO display a cursor here |  | MAKE IT TO DISPLAY A TEXT IN BLACK COLOR | 19/7/2017
4
5
6
7
8
9
10
11
12 | DEFECT_257
13
14
15
16
17
18
19
20
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: