## level1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | Vendor_Master_Client_Subclient_Tab_02
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1 | vendor name | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_258 | 1.)as per a selected name from a drop down belongs to that should display in a grid 2.)if a selected Vendo doesn’t have any client/subclient shouldn’t show anything here | 1.)its working fine where as Selected vendor doesn’t have any Client/Subclient Also it showing a defualt last view Vendor Record list | FAIL | Its shouldn’t display like that make it proper if selected vendor doesn’t have any records clear it | 20/7/2017
2 | SEARCH VENDOR STATE/COUNTY | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_259 | in a place of search area SEARCH VENDOR STATE/COUNTY text label has to be dsiplay | but here there is no label itself displaying | FAIL | display a proper label here | 20/7/2018
3 | refresh button | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_260 | when click on a Refresh button all the data should get refresh by defualt | its working fine but when refresh Cursor has to be display in a Search field by defualt | FAIL | refreshing but no cursor has been displaying | 20/7/2019
4 | refresh | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_261 | when togling from a tab1 to tab 2 pages should automaticaly should get clear | but here a tab1 getting clear and a TAB 2 ntt getting clear vendor name and client/subclient if selected | FAIL | make it to clear al the fields when toggling between tabs | 20/7/2020
5 | Client Grid(sorting) | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_262 | when a record viewing in a client grid should be a in a sorting order | but here records vieewing not in a sorted order | FAIL | make it to display in a sorting order | 20/7/2021
6 | Subclient Grid(sorting) | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_263 | when a record viewing in a client grid should be a in a sorting order | but here records vieewing not in a sorted order | FAIL | make it to display in a sorting order | 20/7/2022
7 | Add SI.NO | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_264 | in a Search grid as per all other forms it should have a SI.No tab | but here it doesn’t have a s.no tab |  | ADD a si.no in a search grid | 20/7/2023
8 | >> Button | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_265 | when this button clicked selected records inserted successfully message has to be display | but here its showing a Record update succesfully when adding itself | FAIL | better make it to cahnge a message text record inserted successfully | 20/7/2024
9 | << button | Vendor_Master_Client_Subclient_Tab_02 | DEFECT_266 | if dint select a any record if I click on this button it should show a Message select any 1 record message | but here its showing a confirmation message and a deleted successfully like so message and at the same time only a particular records belongs to that Vendor will be displaying but a total records wil be showing nt a correct one | FAIL | make it not to display this messagwe here and display a proper total records | 20/7/2025
10
11
12
13
14
15 |  | DEFECT_267
16
17
18
19
20 | DEFECT_267
21
22
23
24
25

## level2
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka:

## Sheet1
DRN OMS DEFECT REPORT
PROJECT NAME |  |  | DRN Order Management System |  | DEFECT REPORT belongs to TEST case Name&No: | OMS _Branch 04
DEFECT REPORT BY |  |  | SHIVARAJ |  | FIXED DEVELOPER | KAVITHA
Sl.No | FEATURE NAME | TEST CASE NO | DEFECT ID | EXPECTED RESULT | ACTUAL RESULT | TESTER STATUS | COMMENTS | TESTED DATE | DEVELOPER STATUS | BUG FIXED DATE | BUG FIXED BY | CROSS TESTED STATUS | CTS DATE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Note on G3: kavita.ka: